## Sheet1
Team Members
Name | Index No | Allocated work
W.S.D. Fernando | 170168K | Mechanics and hardwork
G. Gajanan | 170170J | Programming the PIC micro controller
D.M.D.P. Dissanayake | 170147V
D.M.A.I.Divisekara | 170150A | PCB designs
WEEKLY PLAN
Task |  | Week one | [6 empty] | Week two
|  | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Making the schematic diagrams | Sensors | bar: Week one 15
Motor controllers | bar: Week one 15
Micro controller and power supply | bar: Week one 15
Designing the enclosure using solid works | bar: Week one 15 to Week one 17
Making the layouts of the pcb | Sensors | bar: Week one 16 to Week one 17
Motor controllers | bar: Week one 16 to Week one 17
Micro controller and power supply | bar: Week one 16 to Week one 17
Programming PIC | bar: Week one 18 to Week two 23
Making PCBs | Sensors | bar: Week two 24 to Week two 25
Motor controllers | bar: Week two 24 to Week two 25
Micro controller and power supply | bar: Week two 24 to Week two 25
Testing the PCBs | Sensors | bar: Week two 26
Motor controllers | bar: Week two 26
Micro controller and power supply | bar: Week two 26
Making enclosure | bar: Week two 27 to Week two 28
Assembling Components | bar: Week two 28 to Week two 29
Testing | bar: Week two 29 to Week two 30